## Results Assessment
ADA Guidelines for Programme and Project Evaluations (Annex 9): |  |  |  |  | Results Assessment Form (RAF) template
Attention: This form must be completed for each PP evaluation and submitted together with the evaluation report.
FOR THE EVALUATION MANAGER AND ADA PPM TO FILL IN (Part 1) | [6 empty] | FOR THE EVALUATOR/S TO FILL IN (Part 2)
ADA PP Number | ADA Organizational Unit managing the PP | PP Title | CRS Code/s | Country/Region of PP | Evaluation Manager | Project Budget | Evaluation company/ evaluator | Timing of evaluation | Completion date of evaluation (xx/xx/xxxx) | Assessment of results - key aspects | Score (choose only one answer for each aspect assessed) | Justifiy score. Include finding and reference page/s in evaluation report.
6542-00/2018 | Third-Party Funding International | GRETA / Green Economy: Sustainable Mountain Tourism & Organic Agriculture in Georgia | 32130 - SME development | Georgia | Tekla Nemanishvili | EUR 6.800.000 | DEPA Consulting | Final Evalution | 2024-04-03 | 1. The extent to which the planned ouput/s (as defined in the project document/logframe/Theory of Change) has/have been achieved taking into account the causal link between inputs and outputs. | L (Largely achieved) | Since April 2022, project activities have focused on the achievement of the targets set for indicators of the three outcomes and have recovered most of the previously accumulated delays. Therefore, the planned outputs were largely achieved. (finding 1,1 page 17 of ER)
[10 empty] | 2. The extent to which the planned outcome/s (as defined in the project document/logframe/Theory of Change) has/have been achieved taking into account the causal link between outputs and outcomes. | P (Partly achieved) | Project’s outcomes, in terms of changes and effects, have only partially emerged for 3 main reasons. First, the ambitious dimention of the set outcomes compared to the one of the outcomes. Second, the negative external factors (e.g. COVID outbreak). Third, the short time for maturing the outcomes since several outputs were delivered in the latest stage of Project implementation. (finding 1.2, page 17-18 of ER)
[10 empty] | 3. The extent to which the PP contributed to the objectives at impact level (as defined in the project document/logframe/ToC). | P (Partly achieved) | Insights on the possible future impact of the Project, in terms of first level of changes, have started to emerge within the Project recipients, both farmers and tourism operators. Less evident is the PP impact in terms of facilitating an improvement of the business environment and the creation of new income opportunities in sustainable mountain tourism and organic agriculture. (finding 6,1 and 6,2, page 17 of ER)
[10 empty] | 4. The extent to which the outputs, outcomes and impact achieved contributed to results related to the relevant cross-cutting issues. Please add a justification for each relevant cross-cutting issue. | P (Partly achieved) | The Project has properly addressed the concepts of gender equality and women/girl’s empowerment, social inclusion and environment. It is difficult to assess whether these correct aproach would contribute to results that will last after the end of the project. (finding 2.1 , 8,1 and 8.2, page 18-19 and 22 of ER)
[10 empty] | 5. Have the right approaches - with a view to implementing ADA's overarching principles - been adopted to ensure results achievement? | L (Largely achieved) | As mentioned above the Project has properly addressed the gender, social and evironmental issues as well as the other ADA's overarching principles as no harm, non-discrimination, integrity, fairness, etc. (finding 2.1 page 18-19 of ER

## Guidance on how to fill the RAF
Achievement of Results - Score
F (Fully achieved) | Expected output/outcome/impact, as stated in the PP document, have been fully achieved
L (Largely achieved) | Expected output/outcome/impact, as stated in the PP document, have been achieved to a large extent
P (Partially achieved) | Expected output/outcome/impact, as stated in the PP document, have been only partially achieved, ie to a small extent
N (Not achieved) | Expected output/outcome/impact, as stated in the PP document, have not been achieved
NAP (not applicable) | No output/outcome or impact level results were stated in the project document or the assessment of output/outcome and impact has not been part of the ToRs of the PP evaluation and thus cannot be assessed in the RAF
NAS (not assessed) | The assessment of output/outcome or impact has been part of the ToR, but it was not possible to make a solid assessment.
The level of achievement (F, L, P, N) stated in the RAF must be documented the evaluation report through solid, triangulated evidence. The RAF must include a reference to relevant key findings and evidence in the evaluation report.
In case of NAP, a reference to the project document and it's goal and objectives or the evaluation`s ToR and which criteria were assessed as part of the evaluation, must be included.
In case of NAS, a thorough justification must be included, with reference to the evaluation report, why a solid assessment was not possible.
Language
PP | Programme/Project
Results achievement | Achievements in terms of effectiveness (output and outcome level) and impact.