## Results Assessment
ADA Guidelines for Programme and Project Evaluations (Annex 9): |  |  |  |  | Results Assessment Form (RAF) template
Attention: This form must be completed for each PP evaluation and submitted together with the evaluation report.
FOR THE EVALUATION MANAGER TO FILL IN | [6 empty] | FOR THE EVALUATOR TO FILL IN
ADA PP Number | ADA Organizational Unit managing the PP | PP Title | CRS Code/s | Country/Region of PP | Evaluation Manager | Project Budget | Evaluation company/ evaluator | Timing of evaluation | Completion date of evaluation (xx/xx/xxxx) | Assessment of results - key aspects | Score (choose only one answer for each aspect assessed) | Justifiy score. Include finding and reference page/s in evaluation report. | Comments
2608-00 /2019 | Department Programmes and Projects International, Unit Countries and Regions | Southern African Solar Training and Demonstration Initiative (SOLTRAIN), Phase IV | 23230 - Solar energy for centralised grids | Namibia, Botswana, Zimbabwe, South Africa, Lesotho, Mozambique | Werner Weiss, AEE INTEC | € 3.000.000 | SERA global GmbH | August 9 to December 8 2022 | 2022-11-07 | 1. The extent to which the planned ouput/s (as defined in the project document/logframe/Theory of Change) has/have been achieved taking into account the causal link between inputs and outputs. | F (Fully achieved) | Output 1 - More than 2070 participants in 177 different types of trainings and workshops. Reference page: 8, 17 Output 2 - 159 systems installed and quality checked; in total 345 demonstration systems approved (status 29 September 2022). In total, the number of installed solar thermal demonstration systems which benefit women and marginalized groups in particular is 39 out of 159 installed demonstration systems. Out of 345 solar thermal systems there are 142 systems benefitting women and marginalized groups (status 29 September 2022). Reference page: 9, 11, 17, Output 3 - Annually saved electricity and annually avoided CO2 emissions from 159 installed systems (status 29 September 2022): 854.3 MWh, 269 t CO2. If all the 345 solar thermal systems that have already been approved will be built by the end of the project, these solar thermal systems will save 2,531 MWh/a electricity and will avoid 798 tCO2/a. Reference page: 9, 11, 17,
[10 empty] | 2. The extent to which the planned outcome/s (as defined in the project document/logframe/Theory of Change) has/have been achieved taking into account the causal link between outputs and outcomes. | L (Largely achieved) | Outcome: Implementation of five out of six Solar Thermal Roadmaps is in progress. Reference pages: 17, Annexes II from page 34 on
[10 empty] | 3. The extent to which the PP contributed to the objectives at impact level (as defined in the project document/logframe/ToC). | F (Fully achieved) | Annual statistics of installed systems are available. Annually saved electricity and annually avoided CO2 emissions from 159 installed systems (status 29 September 2022): 854.3 MWh, 269 t CO2. If all the 345 solar thermal systems that have already been approved will be built by the end of the project, these solar thermal systems will save 2,531 MWh/a electricity and will avoid 798 tCO2/a. Reference page: 9, 11, 17,
[10 empty] | 4. The extent to which the outputs, outcomes and impact achieved contributed to results related to the relevant cross-cutting issues. Please add a justification for each relevant cross-cutting issue. | NAS (not assessed)
[10 empty] | 5. Have the right approaches - with a view to implementing ADA's overarching principles - been adopted to ensure results achievement? | NAS (not assessed)

## Guidance on how to fill the RAF
Achievement of Results - Score
F (Fully achieved) | Expected output/outcome/impact, as stated in the PP document, have been fully achieved
L (Largely achieved) | Expected output/outcome/impact, as stated in the PP document, have been achieved to a large extent
P (Partially achieved) | Expected output/outcome/impact, as stated in the PP document, have been only partially achieved, ie to a small extent
N (Not achieved) | Expected output/outcome/impact, as stated in the PP document, have not been achieved
NAP (not applicable) | No output/outcome or impact level results were stated in the project document or the assessment of output/outcome and impact has not been part of the ToRs of the PP evaluation and thus cannot be assessed in the RAF
NAS (not assessed) | The assessment of output/outcome or impact has been part of the ToR, but it was not possible to make a solid assessment.
The level of achievement (F, L, P, N) stated in the RAF must be documented the evaluation report through solid, triangulated evidence. The RAF must include a reference to relevant key findings and evidence in the evaluation report.
In case of NAP, a reference to the project document and it's goal and objectives or the evaluation`s ToR and which criteria were assessed as part of the evaluation, must be included.
In case of NAS, a thorough justification must be included, with reference to the evaluation report, why a solid assessment was not possible.
Language
PP | Programme/Project
Results achievement | Achievements in terms of effectiveness (output and outcome level) and impact.